## Project Planner
Sarcasm Detection System for Hinglish Language
Project Planner |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-06-01 | 2020-06-08 | 2020-06-15 | 2020-06-22 | 2020-06-29 | 2020-07-06 | 2020-07-13 | 2020-07-20 | 2020-07-27 | 2020-08-03 | 2020-08-10 | 2020-08-17 | 2020-08-24 | 2020-08-31 | 2020-09-07 | 2020-09-14 | 2020-09-21 | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Litration Review | 1 | 15 | 1 | 22 | 100%
Research Topic Selection | 3 | 6 | 3 | 7 | 100%
Research Proposal Writing | 8 | 7 | 9 | 7 | 100%
Create a dataset with of 2000 Sent. | 10 | 5 | 10 | 8 | 100%
Research Embedding for Hinglish | 15 | 2 | 15 | 2 | 100%
Finalize Approach | 15 | 3 | 15 | 3 | 100%
Prepare and Submit Interim Report | 23 | 1 | 20 | 5 | 100%
Develop 4+ Models | 15 | 10 | 15 |  | 10%
Evaluate Performance of Models | 25 | 1
Write Final Desertation | 26 | 4
Review Desertation with Guide (1st Review) | 27 | 2
Compare Models/ Conclusion | 28 | 1
Prepare a final Presentation | 29 | 1
Review Desertation with Guide (2nd Review) | 29 | 1
Complete report | 30 | 1